## Report
Test Case Report
Project Name | Daraz Seller Center
Module Name | Sign Up and Sign In |  |  |  |  | Total No. | Status | Result :
Test Case Version | [5 empty] | 43 | PASS
Written By | Farhan Hasin |  |  |  |  | 7 | FAIL
Executed By | Farhan Hasin |  |  |  |  | 12 | Not Executed | New Features | Testing Scope | Testing Environment : | Google Chrome Browser
Reviewed By | Ehsanul Alam Sabbir |  |  |  |  | 0 | Out of Scope
TEST EXECUTION REPORT
Test Case | PASS | FAIL | Not Executed | Out Of Scope | Total TC
| 43 | 7 | 12 | 0 | 62
Grand Total | 43 | 7 | 12 | 0 | 62
LIMITATIONS
Documents |  |  |  | Received | Useful
PRD |  |  |  | No | No
USER STORY |  |  |  | No | No
| Testing Type in Scope | Description
Yes/ No. Justification (If No): | Functional Testing | This type of testing ignores the internal parts and focuses only on the output to check if it is as per the requirement or not.
Yes/ No. Justification (If No): | Integration Testing | Testing of all integrated modules to verify the combined functionality after integration is termed as Integration Testing.
Yes/ No. Justification (If No): | Negative Testing | Testing having the mindset of “attitude to break” using incorrect data and invalid inputs.
Yes/ No. Justification (If No): | Usability Testing | Test application from user friendliness perspective.
Yes/ No. Justification (If No): | Browser Compatibility Testing | Browser Compatibility Testing is performed for web applications and it ensures that the software can run with the combination of different browser and operating system. This type of testing also validates whether web application runs on all versions of all browsers or not.
Yes/ No. Justification (If No): | Boundary Value Testing | There is an upper and lower boundary for each range and testing is performed on these boundary values.
Yes/ No. Justification (If No): | Risk Based Testing Or Regression Testing | Risk-Based Testing includes testing of highly critical functionality, which has the highest impact on business and in which the probability of failure is very high. Testing an application as a whole for the modification in any module or functionality is termed as Regression Testing.

## TestCase
Product Name |  | Daraz Seller Center | TC Start Date | 31/03/2023 | TC Execution Start Date | 2023-02-04 |  |  |  |  | TEST CASE
Module Name |  | Sign Up and Sign In | TC End Date | 2023-01-04 | TC Execution End Date | 2023-03-04 |  |  |  |  | PASS | 43
Epic |  |  | Test Case Developed By | Farhan Hasin | Browser (tested) | Yes |  |  |  |  | FAIL | 7
Developer Name (TL) |  |  | Test Case Reviewed By | Ehsanul Alam Sabbir | Performance (tested) | Yes |  |  |  |  | Not Executed | 12
Test Executed by | [10 empty] | Out of Scope | 0
[11 empty] | TOTAL | 62
#SL | Module | Type of Testing | Features | Test Cases | Exepected Result | Actual Result | Test Data | Reproducing Steps | Bug Screen Shot | Dev Comments | Final Status | Remarks
1 |  | Browser Compatibility Testing |  | Checking by running the site in different browsers | Should run in different browsers | Found as per expectation | Chrome Internet Explorer Mozilla Firefox Microsoft Edge Opera Mini | 1. Goto different browsers 2. Search 'BD Shop' 3. Goto the website |  |  | Passed
2 | User Management | UI Testing | Sign Up | Checking spelling or grammatical mistakes | No spelling or grammatical mistakes | Found as per expectation | N/A | 1. Goto the URL https://www.mobileaction.co/app/android/us/daraz-seller-center/com.daraz.sellercenter 2. Click on Register button at the right corner 3. Check the spelling and grammar of the website |  |  | Passed
3 |  |  |  | Verifying the font, text color and style | Should be as per the requirement | Found as per expectation | N/A | 1. Goto the URL https:https://www.mobileaction.co/app/android/us/daraz-seller-center/com.daraz.sellercenter 2. Click on Register button at the right corner 3. Check the font, text color and style |  |  | Passed
4 |  |  |  | Verifying mandatory field is marked with a red asterisk | Red asterisk should be present | Found as per expectation | N/A | 1. Goto the URL http://www.mobileaction.co/app/android/us/daraz-seller-center/com.daraz.sellercenter 2. Check red asterisk beside mandatory field |  |  | Passed
5 |  |  |  | Checking by hovering over the fields | A text should appear over the fields | Found as per expectation | N/A | 1. Goto the URL https:https://www.mobileaction.co/app/android/us/daraz-seller-center/com.daraz.sellercenter 2. Hover over every fields |  |  | Passed
6 |  |  |  | Checking alignment of the fields | Proper alignment of the fields should be present | Found as per expectation | N/A | 1. Goto the URL https:https://www.mobileaction.co/app/android/us/daraz-seller-center/com.daraz.sellercenter 2. Click on Register button at the right corner 3. Check alignment of the fields |  |  | Passed
7 |  |  |  | Checkbox beside 'Sign Up for Newsletter' | Checkbox should be present | Found as per expectation | N/A | 1. Goto the URL httpshttps://www.mobileaction.co/app/android/us/daraz-seller-center/com.daraz.sellercenter 2. Check checkbox beside 'Sign Up for Newsletter' |  |  | Passed
8 |  |  |  | Checkbox beside 'Remember Me' | Checkbox should be present | Found as per expectation | N/A | 1. Goto the URL https:https://www.mobileaction.co/app/android/us/daraz-seller-center/com.daraz.sellercenter 2. Click on Register button at the right corner 3. Check checkbox beside 'Remember Me' |  |  | Passed
9 |  |  |  | Checking 'Remember Me' checkbox is not enabled by default | Should not be enabled by default | Not found as per expectation | N/A | 1. Goto the URL https:https://www.mobileaction.co/app/android/us/daraz-seller-center/com.daraz.sellercenter 2. Click on Register button at the right corner 3. Check 'Remember Me' checkbox |  |  | Failed
10 |  | Functional Testing |  | Keeping mandatory fields blank | Should be as per the requirement | Sholud not allow user to register and pop an error message | N/A | 1. Goto the URL https:https://www.mobileaction.co/app/android/us/daraz-seller-center/com.daraz.sellercenter 2. Click on Register button at the right corner 3.Keep mandatory fields blank |  |  | Passed
11 |  |  |  | Checking firstname and lastname field is case insensitive | Should accept the provided input | Found as per expectation | N/A | 1. Goto the URL http://www.mobileaction.co/app/android/us/daraz-seller-center/com.daraz.sellercenter 2. Input AbbCCdd and uuXXggDD in firstname and lastname field |  |  | Passed
12 |  |  |  | Entering blank at first position in firstname and lastname field | Should not accept the provided input | Found as per expectation | absnab sndjsdhi | 1. Goto the URL https://www.mobileaction.co/app/android/us/daraz-seller-center/com.daraz.sellercenter 2. Click on Register button at the right corner 3. Input space at first position of firstname and lastname | First blank position error |  | Failed
13 |  |  |  | Entering blank at last position of firstname and lastname field | Should not accept the provided input | Not found as per expectation | agsvgas afcsfas | 1. Goto the URL https:http://www.mobileaction.co/app/android/us/daraz-seller-center/com.daraz.sellercenter 2. Click on Register button at the right corner 3. Input space at last position of firstname and lastname | Last blank position error |  | Failed
14 |  |  |  | Checking alert message for all mandatory fields | Should pop an error message | Not found as per expectation | N/A | 1. Goto the URL https://www.mobileaction.co/app/android/us/daraz-seller-center/com.daraz.sellercenter 2. Click on Register button at the right corner 3. Keeping blank in each field and checking repeatedly |  |  | Passed
15 |  |  |  | Inputing firstname and lastname with special characters | Should not accept the provided input | Not found as per expectation | "@#%$" "=*$" | 1. Goto the URL https://www.mobileaction.co/app/android/us/daraz-seller-center/com.daraz.sellercenter 2. Click on Register button at the right corner 3. Enter special characters in firstname and lastname field | Special Character error |  | Failed
16 |  |  |  | Inputing firstname and lastname with numbers | Should not accept the provided input | Not found as per expectation | 6437467346 74637463476 | 1. Goto the URL https://www.mobileaction.co/app/android/us/daraz-seller-center/com.daraz.sellercenter 2. Click on Register button at the right corner 3. Enter numbers in firstname and lastname field | Numbers error |  | Failed
17 |  |  |  | Inputing firstname and lastname with decimal numbers | Should not accept the provided input | Not found as per expectation | 55.6553 65.585 | 1. Goto the URL https://www.mobileaction.co/app/android/us/daraz-seller-center/com.daraz.sellercenter 2. Click on Register button at the right corner 3. Enter decimal numbers in firstname and lastname field | Decimal Numbers error |  | Failed
18 |  |  |  | Inputing firstname and lastname with alphanumeric characters | Should accept the provided input | Found as per expectation | Farhan22 Hasin77 | 1. Go to the URL https://www.mobileaction.co/app/android/us/daraz-seller-center/com.daraz.sellercenter2. Click on Register button at the right corner 3. Enter alphanumeric characters in firstname and lastname field |  |  | Passed
19 |  |  |  | Inputing firstname and lastname with alphabets | Should accept the provided input | Found as per expectation | Farhan Hasin | 1. Goto the URL https://www.mobileaction.co/app/android/us/daraz-seller-center/com.daraz.sellercenter 2. Click on Register button at the right corner 3. Enter alphabets in firstname and lastname field |  |  | Passed
20 |  |  |  | Entering comma between alphabets for firstname and lastname | Should not accept the provided input | Not found as per expectation | sahs,us Hasin | 1. Goto the URL https://www.mobileaction.co/app/android/us/daraz-seller-center/com.daraz.sellercenter 2. Click on Register button at the right corner 3. Enter comma alphabets in firstname and lastname field | Commas between characters |  | Failed
21 |  |  |  | Entering space between alphabets for firstname and lastname | Should accept the provided input | Found as per expectation | N/A | 1. Goto the URL https://www.mobileaction.co/app/android/us/daraz-seller-center/com.daraz.sellercenter 2. Click on Register button at the right corner 3. Enter space between alphabets in firstname and lastname field |  |  | Passed
22 |  |  |  | Checking newsteller checkbox | Should function successfully | Found as per expectation | N/A | 1. Goto the URL https://www.mobileaction.co/app/android/us/daraz-seller-center/com.daraz.sellercenter 2. Click on Register button at the right corner 3. Select the newsteller checkbox |  |  | Passed
23 |  |  |  | Validating an email id can only be used one time | Should not allow user to register and display a pop message | Found as per expectation with an error message | fhasin60@gmail.com | 1. Goto the URL https://www.mobileaction.co/app/android/us/daraz-seller-center/com.daraz.sellercenter 2. Click on Register button at the right corner 3. Fill the email address with already registered email |  |  | Passed
24 |  |  |  | Checking by inputing invalid email format | Should not accept the provided input and display an error message | Found as per expectation with an error message | hgfhghjgh@yuygh | 1. Goto the URL https://www.mobileaction.co/app/android/us/daraz-seller-center/com.daraz.sellercenter 2. Click on Register button at the right corner 3. Fill the email address with invalid email address format |  |  | Passed
25 |  |  |  | Checking by inputing valid email format | Should accept the provided input | Found as per expectation |  | 1. Goto the URL https://www.mobileaction.co/app/android/us/daraz-seller-center/com.daraz.sellercenter 2. Click on Register button at the right corner 3. Fill the email address with valid email address format |  |  | Not executed
26 |  |  |  | Checking password and confirm field values are masked | Should be masked | Found as per expectation |  | 1. Goto the URL https://www.mobileaction.co/app/android/us/daraz-seller-center/com.daraz.sellercenter 2. Click on Register button at the right corner 3. Enter password and confirm password |  |  | Not executed
27 |  |  |  | Inputing invalid combinations of characters in password and confirm password field | Should not allow user to register and display a pop message | Found as per expectation |  | 1. Goto the URL https://www.mobileaction.co/app/android/us/daraz-seller-center/com.daraz.sellercenter 2. Click on Register button at the right corner 3. Enter invalid combinations of characters in password and confirm password |  |  | Not executed
28 |  |  |  | Inputing weak password length | Should allow user to register | Found as per expectation | 22446688 | 1. Goto the URL https://www.mobileaction.co/app/android/us/daraz-seller-center/com.daraz.sellercenter 2. Click on Register button at the right corner 3. Enter weak password length in password and confirm password |  |  | Passed
29 |  |  |  | Inputing medium password length | Should allow user to register | Found as per expectation | hasinfarhan224466 | 1. Goto the URL https://www.mobileaction.co/app/android/us/daraz-seller-center/com.daraz.sellercenter 2. Click on Register button at the right corner 3. Enter medium password length in password and confirm password |  |  | Passed
30 |  |  |  | Inputing strong password length | Should allow user to register | Found as per expectation | hasinH$#@756 | 1. Goto the URL https://www.mobileaction.co/app/android/us/daraz-seller-center/com.daraz.sellercenter 2. Click on Register button at the right corner 3. Enter strong password length in password and confirm password |  |  | Passed
31 |  |  |  | Inputing different data for password and confirm password | Should not allow user to register and display a pop message | Found as per expectation | Password: farhan@7777 Confirm password: farhan@7777 | 1. Goto the URL https://www.mobileaction.co/app/android/us/daraz-seller-center/com.daraz.sellercenter 2. Click on Register button at the right corner 3. Enter different values in password and confirm password |  |  | Passed
32 |  |  |  | Inputing valid data for password and confirm password | Should allow user to register | Found as per expectation | farhan@7777 | 1. Goto the URL https://www.mobileaction.co/app/android/us/daraz-seller-center/com.daraz.sellercenter 2. Click on Register button at the right corner 3. Enter valid credentals in password and confirm password |  |  | Passed
33 |  |  |  | Selecting 'Remember Me' checkbox to disable | Should disable 'Remember Me' option | Found as per expectation | N/A | 1. Goto the UR https://www.mobileaction.co/app/android/us/darazL 2. Click on Register button at the right corner 3. Disable 'Remember Me' checkbox |  |  | Not Executed
34 |  |  |  | Checking visiting the site again by selecting 'Remember Me' | Should remember credentials | Found as per expectation | N/A | 1. Goto the URL https://www.mobileaction.co/app/android/us/daraz-seller-center/com.daraz.sellercenter 2. Click on Register button at the right corner 3. Fill all the fiels with valid credentials 4. Enable 'Remember Me' 5. Visit the site again |  |  | Not executed
35 |  |  |  | Checking visiting the site again by unselecting 'Remember Me' | Should not remember credentials | Found as per expectation | N/A | 1. Goto the URL https://www.mobileaction.co/app/android/us/daraz-seller-center/com.daraz.sellercenter 2. Click on Register button at the right corner 3. Fill all the fiels with valid credentials 4. Disable 'Remember Me' 5. Visit the site again |  |  | Not executed
36 |  |  |  | Checking captcha inputing invalid data | Should not accept the captcha and pop an error message | Found as per expectation | N/A | 1. Goto the URL https://www.mobileaction.co/app/android/us/daraz-seller-center/com.daraz.sellercenter 2. Click on Register button at the right corner 3. Fill all the fiels with valid credentials 4. Fill invalid data in captcha field |  |  | Not executed
37 |  |  |  | Keeping captcha field blank | Should not enable user to register and pop an error message | Found as per expectation | N/A | 1. Goto the URL https://www.mobileaction.co/app/android/us/daraz-seller-center/com.daraz.sellercenter 2. Click on Register button at the right corner 3. Fill all the fiels with valid credentials 4. Keep captcha field blank |  |  | Not executed
38 |  |  |  | Checking captcha is case insensitive | Should be case insensitive | Found as per expectation | N/A | 1. Goto the URL https://www.mobileaction.co/app/android/us/daraz-seller-center/com.daraz.sellercenter 2. Click on Register button at the right corner 3. Fill all the fiels with valid credentials 4. Fill the captcha with upper and lower case alphabets |  |  | Not executed
39 |  |  |  | Checking new captcha is generated on page reload | Should generate new captcha | Found as per expectation | N/A | 1. Goto the URL https://www.mobileaction.co/app/android/us/daraz-seller-center/com.daraz.sellercenter 2. Click on Register button at the right corner 3. Fill all the fiels with valid credentials 4. Reload the site again |  |  | Not executed
40 |  |  |  | Checking new captcha is generated adding wrong captcha | Should generate new captcha | Found as per expectation | N/A | 1. Goto the URL https://www.mobileaction.co/app/android/us/daraz-seller-center/com.daraz.sellercenter 2. Click on Register button at the right corner 3. Fill all the fiels with valid credentials 4. Input wrong captcha |  |  | Not executed
41 |  |  |  | Checking reload captcha option | Should generate new captcha | Found as per expectation | N/A | 1. Goto the URL https://www.mobileaction.co/app/android/us/daraz-seller-center/com.daraz.sellercenter 2. Click on Register button at the right corner 3. Fill all the fiels with valid credentials 4. Reload captcha |  |  | Not executed
42 |  |  |  | Checking captcha inputing valid data | Should allow user to register | Found as per expectation | N/A | 1. Goto the URL https://www.mobileaction.co/app/android/us/daraz-seller-center/com.daraz.sellercenter 2. Click on Register button at the right corner 3. Fill all the fiels with valid credentials 4. Input valid captcha |  |  | Not executed
43 |  |  |  | Checking registration with invalid email address | Should not allow user to register and pop an error message | Not found as per expectation | Firstname: Farhan Lastname: Hasin Email: hdfd@gmail.com Password: 224466 Confirm Password: 224466 | 1. Goto the URL https://www.mobileaction.co/app/android/us/daraz-seller-center/com.daraz.sellercenter 2. Click on Register button at the right corner 3. Fill all the fiels with invalid credentials 4.Click 'Create an Account' | Invalid email address |  | Failed
44 |  |  |  | Checking registration button with valid credentials | Should allow user to register | Found as per expectation | N/A | 1. Goto the URL https://www.mobileaction.co/app/android/us/daraz-seller-center/com.daraz.sellercenter 2. Click on Register button at the right corner 3. Fill all the fiels with valid credentials 4.Click 'Create an Account' |  |  | Passed
45 |  |  |  | Checking confirmation mail sent to the registered email | Sent successfully | Found as per expectation | N/A | 1. Goto the URL https://www.mobileaction.co/app/android/us/daraz-seller-center/com.daraz.sellercenter 2. Click on Register button at the right corner 3. Fill all the fiels with valid credentials 4.Click 'Create an Account' 5. Check mail and confirm account |  |  | Passed
46 |  |  |  | Checking 'Sign in with Facebook' | Should allow user to register | Found as per expectation | Click on 'Sign in with Facebook' | 1. Goto the URL https://www.mobileaction.co/app/android/us/daraz-seller-center/com.daraz.sellercenter 2. Click on Register button at the right corner 3. Click on 'Sign in with Facebook' |  |  | Passed
47 |  |  |  | Checking 'Sign in with Google' | Should allow user to register | Found as per expectation | Click on 'Sign in with Google' | 1. Goto the URL https://www.mobileaction.co/app/android/us/daraz-seller-center/com.daraz.sellercenter 2. Click on Register button at the right corner 3. Click on 'Sign in with Google' |  |  | Passed
48 |  | Usability Testing |  | Checking copy paste functionality in every field | Should copy and paste text from fields | Functioning successfully | N/A | 1. Goto the URL https://www.mobileaction.co/app/android/us/daraz-seller-center/com.daraz.sellercenter 2. Click on Register button at the right corner 3. Copy paste text in every field |  |  | Passed
49 |  |  |  | Checking keyboard tab button functionality | Should switch to another field and highlight text | Functioning successfully | Enter tab in every field | 1. Goto the URL https://www.mobileaction.co/app/android/us/daraz-seller-center/com.daraz.sellercenter 2. Click on Register button at the right corner 3. Enter tab in every field |  |  | Passed
50 |  |  |  | Checking keyboard enter button functionality | Should switch to another field | Functioning successfully | Input Enter in every field | 1. Goto the URL https://www.mobileaction.co/app/android/us/daraz-seller-center/com.daraz.sellercenter 2. Click on Register button at the right corner 3. Enter enter in every field |  |  | Passed
51 |  | Functionality Testing | Sign In | Keeping email and password field blank | Should not allow user to login and display an error messeage | Found as per expectation | N/A | 1. Goto the URL https://www.mobileaction.co/app/android/us/daraz-seller-center/com.daraz.sellercenter 2. Click on login button at the right corner 3. Keep both the fields blank |  |  | Passed
52 |  |  |  | Checking if the data in password is masked | Should be masked | Found as per expectation | farhan@8888 | 1. Goto the URL https://www.mobileaction.co/app/android/us/daraz-seller-center/com.daraz.sellercenter 2. Click on login button at the right corner 3. Input values in password field and check if it is masked |  |  | Passed
53 |  |  |  | Checking login wrong credentials in email and password field | Should not allow user to login and display an error messeage | Found as per expectation | fgcfh@nndj.com hdjui44 | 1. Goto the URL https://www.mobileaction.co/app/android/us/daraz-seller-center/com.daraz.sellercenter 2. Click on login button at the right corner 3. Input invalid credentials in email and password field |  |  | Passed
54 |  |  |  | Checking login valid credentials in email and password field | Should allow user to register | Found as per expectation | N/A | 1. Goto the URL https://www.mobileaction.co/app/android/us/daraz-seller-center/com.daraz.sellercenter 2. Click on login button at the right corner 3. Input valid credentials in email and password field |  |  | Passed
55 |  |  |  | Verifying ‘Forgot Password’ functionality | Should sent an email for recovering password | Found as per expectation | N/A | 1. Goto the URL https://www.mobileaction.co/app/android/us/daraz-seller-center/com.daraz.sellercenter 2. Click on login button at the right corner 3.Click on 'Forgot Password' 4. Check email |  |  | Passed
56 |  |  |  | Checking by selecting ‘Forgot Password’ multiple times | Account should be temporarily restricted and a message should be displayed | Found as per expectation with a message | N/A | 1. Goto the URL https://www.mobileaction.co/app/android/us/daraz-seller-center/com.daraz.sellercenter 2. Click on login button at the right corner 3.Click on 'Forgot Password' multiple times |  |  | Passed
57 |  |  |  | Verifying change the password link is sent to valid email address | Should be sent to valid email address | Found as per expectation | N/A | 1. Goto the URL https://www.mobileaction.co/app/android/us/daraz-seller-center/com.daraz.sellercenter 2. Click on login button at the right corner 3.Click on 'Forgot Password' 4. Check the registered email |  |  | Passed
58 |  |  |  | Verifying the functionality of 'Set a New Password' | Should provide a new input for setting new password | Found as per expectation | N/A | 1. Goto the URL https://www.mobileaction.co/app/android/us/daraz-seller-center/com.daraz.sellercenter 2. Click on login button at the right corner 3.Click on 'Forgot Password' 4. Check the registered email 5. Click on 'Set up a New Password' |  |  | Passed
59 |  |  |  | Enabling the 'Show Password' checkbox of 'Set a New Password' | Password should be dispayed | Found as per expectation | N/A | 1. Goto the URL https://www.mobileaction.co/app/android/us/daraz-seller-center/com.daraz.sellercenter 2. Click on login button at the right corner 3.Click on 'Forgot Password' 4. Check the registered email 5. Click on 'Set up a New Password' 6. Enable 'Show Password' checkbox |  |  | Passed
60 |  |  |  | Verifying inputing old password on 'Set a New Password' | Should not allow user to login and display an error message | Found as per expectation with an error message | N/A | 1. Goto the URL https://www.mobileaction.co/app/android/us/daraz-seller-center/com.daraz.sellercenter 2. Click on login button at the right corner 3.Click on 'Forgot Password' 4. Check the registered email 5. Click on 'Set up a New Password' 6. Enter old password |  |  | Passed
61 |  |  |  | Verifying login with the newly changed password | Should allow user to login | Found as per expectation | N/A | 1. Goto the URL https://www.mobileaction.co/app/android/us/daraz-seller-center/com.daraz.sellercenter 2. Click on login button at the right corner 3.Click on 'Forgot Password' 4. Check the registered email 5. Click on 'Set up a New Password' 6. Enter new password 7. Click on login |  |  | Passed
62 |  |  |  | Checking if the link gets dissolved setting a new password | Link should get dissolved | Found as per expectation | N/A | 1. Goto the URL https://www.mobileaction.co/app/android/us/daraz-seller-center/com.daraz.sellercenter 2. Click on login button at the right corner 3.Click on 'Forgot Password' 4. Check the registered email 5. Click on 'Set up a New Password' 6. Enter new password 7. Click on 'Create New password' |  |  | Passed
|  |  | Improvement Scopes | 'Remember Me' checkbox should be selected according to user
A maximum length of the password should be defined
Place 'Whats this?' below 'Remember Me'
Place 'Forgot your password' link below Password field
Negative test

## Bug Report
Bug Reporting
# SL 43
Issue: Registered with invalid email address
Reproducing Steps:
1. Goto the URL https://www.mobileaction.co/app/android/us/daraz-seller-center/com.daraz.sellercenter 2. Click on login button at the right corner 3. Fill all the fiels with invalid credentials 4.Click 'Create an Account'
Env: Production
Module: Sign Up
Severity: P1
Screenshot: Invalid email address error
Responsible QA: Farhan Hasin

## Test Metrics
Test Metrics
#SL | Metrics | Description | Result (%)
1 | Percentage of Test Cases Executed | (No. of Test Cases Executed / Total no. of Test Cases Written) * 100 | (62/62)*100 = 100
2 | Percentage of Test Cases Not Executed | (No. of Test Cases not Executed / Total no. of Test Cases Written) * 100 | (12/62)*100 = 19.35
3 | Percentage of Test Cases Passed | (No. of Test Cases Passed / Total no. of Test Cases Executed) * 100 | (43/62)*100 = 69.35
4 | Percentage of Test Cases Failed | (No. of Test Cases Failed / Total no. of Test Cases Executed) * 100 | (7/62)*100 = 11.29
5 | Percentage of Test Cases Blocked | (No. of Test Cases Blocked / Total no. of Test Cases Executed) * 100 | (0/62)*100 = 0
6 | Defect Density | No. of Defects found / Size (No. of Requirements) | N/A
7 | Defect Removal Efficiency (DRE) | (Fixed Defects / (Fixed Defects + Missed Defects)) * 100 | N/A
8 | Defect Leakage | (No. of Defects found in UAT/ No. of Defects found in Testing) * 100 | N/A
9 | Defect Rejection Ratio | (No. of Defects Rejected/ Total no. of Defects Raised) * 100 | N/A
10 | Defect Age | Fixed date - Reported date | N/A
11 | Customer Satisfaction | No. of complaints per Period of Time | N/A